Gage Peterson June 3rd

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Current | Start Date | | | Stop Date | | | Number of Hours | | |
| tasks | Status | proposed | modified | actual | proposed | modified | actual | proposed | modified | actual |
| 1. Preliminary research and proposal preparation | Compleated | Apr 20 | not | Apr 20 | Apr 30 | May 16 | May 16 | 8 | not | 8 |
| 2. Research | Compleated | May 1 | not | May 1 | May 15 | May 17 | May 17 | 16 | 10 | 10 |
| 3. Requirements Specification document | In progress | Apr 16 | May 13 | May 13 | Jun 15 | Jun 8 |  | 31 | not | 24 |
| 4. Design | Not started | Jun 16 | Jun 3 |  | Jul 16 | not |  | 39 | not |  |
| 5. Writing behavior driven tests. | Not started | Jul 17 | not |  | Apr 24 | not |  | 16 | not |  |
| 6. Writing the code | Not started | Aug 1 | not |  | Sep 12 | not |  | 47 | not |  |
|  |  |  |  |  |  |  |  |  |  |  |
| **total hours** |  |  |  |  |  |  |  | **157** | **10** | **42** |
| Accomplishments | | | | | | | | | | |
| Made some progress on the requirements document | | | | | | | | | | |
|
|
| Problems | | | | | | | | | | |
| - Need to make sure that my requirements document is enough | | | | | | | | | | |
|
|
| Changes in Scope, Schedule, and Cost | | | | | | | | | | |
| Changed the due date for the Requirements document because I think I can get it done earlier. | | | | | | | | | | |
|
|
| Confessional | | | | | | | | | | |
| Increase in actual hours since last update: 18  Total anticipated actual hours (at the end of the project): 157  Behind schedule / On schedule / Ahead of schedule: A little ahead. | | | | | | | | | | |
|
|
| Scripture | | | | | | | | | | |
| The laws and requirements that God gives to mankind, either individually or collectively. Keeping the commandments will bring blessings of the Lord to the obedient (D&C 130:21). | | | | | | | | | | |
|
|