Gage Peterson - Wed Apr 29th

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Current | Start Date | | | Stop Date | | | Number of Hours | | |
| tasks | Status | proposed | modified | actual | proposed | modified | actual | proposed | modified | actual |
| 1. Preliminary research and proposal preparation | Complete | Apr 20 | not | Apr 20 | Apr 30 | not | Apr 29 | 8 | 12 | 10 |
| 2. Research | Not started | May 1 | not |  | May 15 | not |  | 16 | not |  |
| 3. Requirements Specification document | Not started | Apr 16 | not |  | Jun 15 | not |  | 31 | not |  |
| 4. Design | Not started | Jun 16 | not |  | Jul 16 | not |  | 39 | not |  |
| 5. Writing behavior driven tests. | Not started | Jul 17 | not |  | Apr 24 | not |  | 16 | not |  |
| 6. Writing the code | Not started | Aug 1 | not |  | Sep 12 | not |  | 47 | not |  |
|  |  |  |  |  |  |  |  |  |  |  |
| **total hours** |  |  |  |  |  |  |  | **157** | **12** | **10** |
| Accomplishments | | | | | | | | | | |
| - Got my proposal approved | | | | | | | | | | |
|
|
| Problems | | | | | | | | | | |
| Getting this class figured out and making sure my scope is good. | | | | | | | | | | |
|
|
| Changes in Scope, Schedule, and Cost | | | | | | | | | | |
| These were all created this time round so not yet! | | | | | | | | | | |
|
|
| Confessional | | | | | | | | | | |
| Increase in actual hours since last update: 2  Total anticipated actual hours (at the end of the project): 162  Ahead of schedule | | | | | | | | | | |
|
|
| Scripture | | | | | | | | | | |
| 1st Nephi 2:4  "And it came to pass that he departed into the wilderness. And he left his house, and the land of his inheritance, and his gold, and his silver, and his precious things, and took nothing with him, save it were his family, and provisions, and tents, and departed into the wilderness." | | | | | | | | | | |
|
|